## 01 README
Document | Multi-Standard Programme Workbook (5-Standard)
Purpose | Combines SOC 2 + PCI DSS v4.0 (existing joint programme) with DPDP Act 2023, ISO/IEC 27001:2022, and NIST CSF 2.0. Single evidence repository, single SteerCo, single dashboard. This follows the strategic decision documented in the Board Memo (NBFC/2026/CISO/JOINT-PROG/001) and adds three more standards in the same programme structure.
Why expand | Many NBFC clients ask for 2-3 of these standards simultaneously. A bank co-issuer asks for SOC 2 + PCI + ISO 27001; an EU customer contract adds DPDP/GDPR; RBI IT Framework 2023 reads almost like NIST CSF. Running five separate programmes is impossible. Running a single merged programme saves 40% engineer-hours vs five separate runs.
Tabs in this workbook
01 README - this page.
02 Standards Map - high-level comparison of 5 standards' purpose & audience.
03 Tags & Cadence - tag legend across all 5 standards; cadence alignment.
04 SOC 2 <-> DPDP - SOC 2 Privacy + DPDP Act 2023 crosswalk.
05 SOC 2 <-> ISO - SOC 2 to ISO 27001:2022 crosswalk.
06 SOC 2 <-> NIST - SOC 2 to NIST CSF 2.0 crosswalk.
07 PCI <-> ISO <-> NIST - Payment-card + ISO 27001 + NIST CSF crosswalk.
08 DPDP <-> ISO <-> NIST - Privacy + ISO + NIST crosswalk.
09 Combined Master Checklist - 100 dedup'd controls across all 5 standards.
10 Policy Register - 70 documents required across the programme.
11 Project Plan - 24-month multi-standard roadmap.
12 Evidence Catalog - 50 artefacts cross-tagged.
13 Vendor Register - vendors with SOC 2 + PCI AOC + ISO + DPDP obligations.
14 Multi-Audit-Trail Q&A - 40 questions covering all 5 standards.

## 02 Standards Map
Standard | Geographic focus | Who cares | Cadence | Type
SOC 2 (AICPA SSAE-18) | Global | Enterprise customers (banks, B2B SaaS, marketplaces) | Annual Type II (12-mo window) | Attestation report
PCI DSS v4.0 (PCI SSC) | Global (acquirer/issuer-driven) | Card networks, acquirer | Annual ROC; quarterly ASV | Site-data security standard + QSA attestation
DPDP Act 2023 | India | All Indian data principals; consent+rights regime | Continuous + breach 72h | Statutory Act (data fiduciary obligations)
ISO/IEC 27001:2022 | Global | Enterprise customers (often EU / BFSI); regulatory foundations also IMD/IRDAI | 3-year certification + annual surveillance | Certifiable ISMS
NIST CSF 2.0 | US (but globally used) | RBI IT Framework 2023 + US/UK B2B + auditor mappings | Continuous improvement + annual maturity | Framework profile

## 03 Tags & Cadence
Tag | Meaning | NBFC example | Audit cadence | Coverage recommendation
UNIVERSAL | Control satisfies all 5 standards. | MFA everywhere, encryption, IAM, IR, audit logging | Continuous+quarterly | Use the strictest cadence (PCI's 12-month log; SOC 2 quarterly review)
MOSTLY-SHARED | Covers 3-4 standards; minor gap on one. | Vendor SP register (All except NIST which is framework-only) | Per cycle varies | Add ISO 27001 risk treatment table to satisfy
STANDARD-SPECIFIC | Lives in one standard's domain. | DPDP data principal access workflow | Per standard | Document separately if needed
DIFFERENTIATED | Same activity, different cadence/evidence. | Logging retention (PCI 12m vs SOC 2 flexible vs ISO unspecified) | Annual + continuous | Tighten to the most demanding cadence

## 04 SOC 2 vs DPDP
SOC 2 | DPDP Act 2023 | Tag | Combined control | Owner | NBFC context
CC1.1 - Integrity/Ethics | S.4 - Notice | MOSTLY-SHARED | Code of Conduct + Privacy Notice + Annual acknowledgement | CISO + DPO | DPDP notice is functionally distinct; combine filing.
CC2.2 - Internal Communication | S.4 - Notice | MOSTLY-SHARED | Unified internal awareness programme with consent flow | CISO + DPO | Notice behaviour modelled per DPDP §4
CC2.3 - External Communication | S.6 - Purpose limitation | STANDARD-SPECIFIC | Privacy notice at layer; consent management on web/app | DPO + Legal | DPDP purposes must be SPECIFIC + lawful
CC3.2 - Risk Assessment | S.10 - Data fiduciary duties | MOSTLY-SHARED | Risk register with DPDP obligations for Significant Data Fiduciary | CISO + DPO | DPDP requires DPIA for high-risk processing
CC5.3 - Policy Deployment | S.10 - Security safeguards | UNIVERSAL | Privacy Policy + Information Security Policy merged | CISO + Legal | DPDP requires 'reasonable security'
CC6.1 - Identity & Access | S.10 - Security safeguards | UNIVERSAL | Same IAM+ MFA; DPDP requires 'appropriate' security | CISO + IAM Lead | Documented by TRA
CC6.6 - Encryption (transit + rest) | S.10 - Security safeguards | UNIVERSAL | AES-256 + TLS 1.3; documented in DPDP §10 audit | Crypto Lead | Significant Data Fiduciary encrypts
P1.1 - Privacy notice | S.4 - Notice | STANDARD-SPECIFIC | Consent+Receipt workflow with withdrawal endpoint | DPO | Direct DPDP mapping
P2.1 - Purpose limitation | S.4 + S.6 - Notice + Purpose | STANDARD-SPECIFIC | Purpose tag in data processing record + UI label | DPO + Eng | DPDP limits retention vs purpose
P3.1 - Retention | S.7 - Storage limitation | STANDARD-SPECIFIC | Retention rule per data class + automated purge | DPO | DPDP limits retention to purpose
P5.1 - Data Subject Access | S.8 - Data Principal Rights | STANDARD-SPECIFIC | Data Principal Rights workflow via portal | DPO + Support | DPDP mandates rights - access, correction, erasure, grievance
CC7.4 - Incident Response | DPDP S.8 - Breach notify 72h | MOSTLY-SHARED | Single IRP with DPDP 72h clock + RBI 2h + PCI acquirer 24h | CISO + Legal | DPDP requires breach notification to Board + affected data principals

## 05 SOC 2 vs ISO 27001
SOC 2 | ISO 27001 Annex A control | Tag | Combined control | NBFC note
CC1.1 - Integrity/Ethics | A.5.1 Policies for information security | UNIVERSAL | Single Information Security Policy | ISO 27001 anchors policy hierarchy
CC1.2 - Board Oversight | A.5.2 Information security roles | MOSTLY-SHARED | Single cyber committee | ISO requires role definitions
CC2.x - Communication | A.5.11 Acceptable use of information assets | MOSTLY-SHARED | Policy library + acknowledgement | ISO requires documented communication
CC3.2 - Risk Assessment | A.6.1.2 Information security risk assessment | UNIVERSAL | Unified risk methodology; ISO mandatory ART + CRR | ISO needs Asset Register + Risk Treatment
CC4.x - Monitoring | A.5.35 Independent review | MOSTLY-SHARED | Internal audit + CCO dashboard | ISO needs independent review
CC5.2 - Tech controls | A.8.9 Configuration management | UNIVERSAL | Same baseline config procedure + change management | ISO Annex A now has tech controls
CC6.1 - Logical Access | A.8.2 Privileged access rights + A.8.5 Secure authentication | UNIVERSAL | Same SSO + MFA; ISO adds PAM for privileged access | ISO mandatory criteria on MFA
CC6.2 - New user access | A.8.2(a),(b) | UNIVERSAL | JML workflow | ISO requires provision + de-provision process
CC6.6 - Encryption | A.8.24 Cryptography | UNIVERSAL | Same KMS + HSM; ISO requires CRY key management documented | ISO prescribes use of crypto
CC7.1 - Vulnerability | A.8.8 Management of technical vulnerabilities | UNIVERSAL | Same scanner + SLA | ISO requires vuln schedule
CC7.4 - Incident Response | A.5.24 Information security incident management planning | UNIVERSAL | Same IR plan + tabletops | ISO mandatory document & plan
CC7.5 - BCP / DR | A.5.30 ICT readiness for business continuity | UNIVERSAL | Same DR plan + tests | ISO mandatory
CC8.1 - Change management | A.8.32 Change management | UNIVERSAL | Same CAB + records | ISO requires change procedure
CC9.2 - Vendor risk | A.5.19 Information security in supplier relationships | MOSTLY-SHARED | Single SP register + AOC | ISO requires supplier agreements + assessment
A1.3 - DR Test | A.5.30 + A.8.14 Testing | UNIVERSAL | Annual DR drill evidence | ISO mandatory; SOC 2 also
C1.x - Confidentiality | A.5.12 Classification of information + A.8.10 Information deletion | UNIVERSAL | Same data classification scheme + tagging | NBFC: PAN = Restricted top tier
PI1.x - Processing integrity | A.8.28 Secure coding | MOSTLY-SHARED | Secure SDLC + change control | ISO requires secure coding
P1.x - Privacy | A.5.34 Privacy & PII protection | STANDARD-SPECIFIC | Privacy notice + consent workflow (separate from DPDP) | ISO vs DPDP both require notice

## 06 SOC 2 vs NIST CSF 2.0
SOC 2 | NIST CSF Function / Category | Tag | Combined control | NBFC note
CC1.x - Governance | GV (Govern): organisational context and risk strategy | UNIVERSAL | Single cyber committee + governance charter | NIST 2.0 added GV - perfect SOC 2 CC1.x overlap
CC2.x - Comms | GV.OC (governance in org context); PR.AT (awareness training) | UNIVERSAL | Same internal + external comms + training | NIST PR.AT mirrors CC2
CC3.2 - Risk Assessment | GV.RM (risk management strategy); ID.RA (risk assessment) | UNIVERSAL | Same risk register | NIST 2.0 aligned with ISO 27005
CC4.1-2 - Monitoring | DE.CM (continuous monitoring); ID.AM (asset management) | UNIVERSAL | Same KPI dashboard | NIST provides inventory category
CC5.3 - Policies | GV.PO (organisational policies) | UNIVERSAL | Same policy library | NIST 2.0 formalised policies
CC6.1 - Logical Access | PR.AA (Identity, Authentication, Access Control) | UNIVERSAL | Same IAM + MFA + RBAC | NIST 2.0 redesign of PR.AC
CC6.6 - Encryption | PR.DS (Data Security) | UNIVERSAL | Same crypto + HSM | NIST 2.0 expanded DS
CC6.8 - Malware | PR.PS (Platform security) - malware | UNIVERSAL | Same EDR | NIST splits platform security
CC7.1 - Vulnerability | ID.RA + DE.CM - vulnerabilities | UNIVERSAL | Same vuln programme | NIST provides explicit category
CC7.2 - Monitoring | DE.AE (anomalies and events); DE.CM | UNIVERSAL | Same SIEM | NIST 2.0 splits DE
CC7.4 - Incident Response | RS.RP (response planning); RS.MI (mitigation); RS.CO (comm) | UNIVERSAL | Same IRP + runbooks + tabletop | NIST 2.0 more structured than v1.1
CC7.5 / A1.3 - Recover | RC.RP (recovery planning); RC.IM (improvement) | UNIVERSAL | Same DR plan + lessons-learned | NIST's RC matches SOC 2 + ISO
CC9.2 - Vendor risk | GV.SC (cyber supply chain risk management) | UNIVERSAL | Same SP register + AOC | NIST 2.0 added GV.SC
CC9.1 - Insurance - not NIST | n/a | MOSTLY-SHARED | Cyber insurance policy + RBI requirement | SOC 2 CC9.1; no NIST equivalent but document separately

## 07 PCI vs ISO vs NIST
PCI Req | ISO 27001 | NIST CSF 2.0 | Tag | Combined | NBFC note
Req 1 - Network Security Controls | A.8.20 Network security; A.8.22 Segregation | PR.IR (Infrastructure resilience); PR.PS - network | MOSTLY-SHARED | Single network policy + segmentation | NBFC: CDE VPC isolated
Req 3 - Protect stored data | A.8.24 Cryptography + A.8.10 Deletion | PR.DS (Data Security) | MOSTLY-SHARED | Card vault encryption + KMS + HSM | PCI specifics for PAN handling
Req 4 - Transmission | A.8.24 Cryptography (transport) | PR.DS | MOSTLY-SHARED | TLS 1.2+ enforced | Same TLS standard ACL across NBFC
Req 5 - Anti-malware | A.8.7 Protection against malware | PR.PS | UNIVERSAL | Same EDR + Linux | CrowdStrike / SentinelOne everywhere
Req 6 - Secure systems | A.8.28 Secure coding + A.8.9 Configuration management | PR.PS + PR.DV - secure dev | MOSTLY-SHARED | Same SDLC + code review | Testing on payment flows
Req 7 - Restrict by need | A.5.15 Access control + A.8.2 | PR.AA | UNIVERSAL | Same RBAC | Card vault access strictly limited
Req 8 - Auth + MFA | A.5.17 Authentication info + A.5.18 Access rights | PR.AA - MFA | MOSTLY-SHARED | Same SSO + WebAuthn + 3DS2 | WebAuthn staff / 3DS2 customers
Req 9 - Physical | A.7 Physical security | PR.AA - physical | MOSTLY-SHARED | Same physical security procedure | PCI adds POI specifics
Req 10 - Logging | A.8.15 Logging + A.5.28 Evidence collection | DE.AE + DE.CM | UNIVERSAL | Same SIEM + log retention | PCI 12-mo; ISO unspecified; NIST unspecified - safer to use PCI
Req 11 - Test regularly | A.8.8 Vuln mgmt + A.8.16 Monitoring + A.5.35 Review | ID.RA + DE.CM | UNIVERSAL | Same pen-test + scans + ASV | Single vendor for both
Req 12 - Org policies | A.5.1 to A.5.39 - organisational policies (entire A.5) | GV.PO | UNIVERSAL | Same policy library | Nearly identical coverage

## 08 DPDP vs ISO vs NIST
DPDP Act § | ISO 27001 | NIST CSF 2.0 | Tag | Combined | NBFC note
§4 Notice | A.5.34 Privacy + A.5.32 IP rights | GV.OC (organisational context) | STANDARD-SPECIFIC | Privacy notice + consent receipt | DPDP sharper; ISO generic
§6 Purpose limitation | A.5.34 | ID.AM asset mgmt | STANDARD-SPECIFIC | Purpose tag in data classification | DPDP requires SPECIFIC purposes
§7 Storage limitation | A.8.10 Information deletion | PR.IP | STANDARD-SPECIFIC | Auto-purge + retention register | Note DPDP max retention
§8 Data Principal Rights | A.5.34 | GV.OC | STANDARD-SPECIFIC | Portal + ticketing workflow | DPDP legally enforceable rights
§10 Security safeguards | A.5.15-A.5.18 + A.8.24 | PR.AA + PR.DS | UNIVERSAL | Same IAM + crypto + SIEM | CISO + DPO alignment
§13 DPIA | A.5.7 Threat intel + A.5.30 | GV.RM + ID.RA | STANDARD-SPECIFIC | DPIA + TRA shared template | Significant Data Fiduciary required
§14 Cross-border | A.5.21 Managing info security in supplier relationships | GV.SC | STANDARD-SPECIFIC | Region-lock + SCP rules | RBI prohibits to non-notified countries
§72h breach | A.5.24-A.5.27 Incident mgmt | RS.CO | UNIVERSAL | Single IR plan with DPDP 72h clock | Multiple clock triggers; one IRP
§16 Cross-border transfer | A.8.21 Data leakage prevention | PR.IP | STANDARD-SPECIFIC | DSPM + region-lock | Region enforcement policy
§26 Penalties | Internal compliance | GV.RM (verification) | MOSTLY-SHARED | Compliance dashboard + internal audit | ₹250 crore penalty avoidance

## 09 Master Checklist
# | Domain | Control | Tag | Standards covered | Cadence | Owner
1 | Governance | Information Security Policy | UNIVERSAL | All 5 | Annual | CISO
2 | Governance | Cyber Committee charter + Board minutes | UNIVERSAL | SOC 2 + ISO + NIST (RBI) | Quarterly | CISO
3 | Governance | Risk assessment methodology | UNIVERSAL | SOC 2 + PCI + ISO + NIST + DPDP | Annual | CRO + CISO
4 | Governance | Cybersecurity operational risk register | UNIVERSAL | SOC 2 + ISO + NIST + DPDP | Quarterly | CISO
5 | Governance | Statement of Applicability (SoA) | STANDARD-SPECIFIC | ISO 27001 only | Annual | CISO
6 | Governance | Risk Treatment Plan (RTP) | STANDARD-SPECIFIC | ISO 27001 only | Annual | CISO
7 | Governance | Internal audit programme + charter | UNIVERSAL | SOC 2 + ISO + NIST | Annual | Internal Audit
8 | Governance | Management review (MRM) for ISMS | STANDARD-SPECIFIC | ISO 27001 only | Quarterly | CISO
9 | IAM | Identity provider (Okta/Entra) with MFA | UNIVERSAL | All 5 | Continuous | IAM Lead
10 | IAM | Privileged Access Management | UNIVERSAL | SOC 2 + ISO + PCI + NIST | Continuous | IAM Lead
11 | IAM | FIDO2 / WebAuthn phishing-resistant MFA | UNIVERSAL | SOC 2 + PCI + ISO + NIST | Continuous | IAM Lead
12 | IAM | Joiners / Movers / Leavers workflow | UNIVERSAL | All 5 | Continuous | IT + HR
13 | IAM | Quarterly access reviews | MOSTLY-SHARED | SOC 2 + ISO + PCI + NIST | Quarterly | Business unit heads
14 | IAM | RBAC + Just-In-Time elevation | UNIVERSAL | SOC 2 + PCI + ISO + NIST | Continuous | IAM Lead
15 | IAM | Service account inventory + Secrets Manager | UNIVERSAL | SOC 2 + PCI + IAM + ISO + NIST | Continuous | Cloud + AppSec
16 | Crypto | Encryption at rest (AES-256, KMS managed) | UNIVERSAL | All 5 | Continuous | Crypto Lead
17 | Crypto | TLS 1.2+ enforced at perimeter | UNIVERSAL | SOC 2 + PCI + ISO + NIST | Continuous | Network Lead
18 | Crypto | Annual key rotation + dual control | MOSTLY-SHARED | SOC 2 + PCI + ISO + NIST | Annual | Crypto Lead
19 | Crypto | HSM (CloudHSM FIPS 140-2 L3) | MOSTLY-SHARED | PCI + ISO + NIST | Continuous | Crypto Lead
20 | Crypto | Card vault tokenisation (VTS+MDES+R-T-V) | STANDARD-SPECIFIC | RBI Tokenisation | Continuous | CTO
21 | Network | Network Security Controls (NSC) | UNIVERSAL | SOC 2 + PCI + ISO + NIST | Continuous | Network Lead
22 | Network | Default-deny firewall rules | UNIVERSAL | SOC 2 + PCI + ISO + NIST | Continuous | Network Lead
23 | Network | Segmentation of CDE | MOSTLY-SHARED | PCI + ISO + NIST | Continuous | Network Lead
24 | Network | WAF at perimeter + payment route | MOSTLY-SHARED | SOC 2 + PCI + ISO + NIST | Continuous | AppSec
25 | Network | IDS / IPS at perimeter | MOSTLY-SHARED | SOC 2 + ISO + NIST | Continuous | SecOps
26 | Network | TLS scan quarterly | MOSTLY-SHARED | SOC 2 + PCI + ISO + NIST | Quarterly | SecOps
27 | AppSec | Secure SDLC policy | UNIVERSAL | SOC 2 + PCI + ISO + NIST | Annual | CTO
28 | AppSec | SAST / SCA per build | MOSTLY-SHARED | SOC 2 + PCI + ISO + NIST | Continuous | AppSec
29 | AppSec | DAST weekly | MOSTLY-SHARED | SOC 2 + PCI + ISO + NIST | Weekly | AppSec
30 | AppSec | 3DS2 for online card transactions | STANDARD-SPECIFIC | PCI + RBI tokenisation | Continuous | Payments Eng
31 | AppSec | Script inventory + Subresource Integrity | STANDARD-SPECIFIC | PCI 6.4.3 / 11.6.1 | Weekly | AppSec
32 | AppSec | Ransomware simulation | STANDARD-SPECIFIC | RBI 2h breach | Annual | CISO
33 | AppSec | Penetration test (annual + on-change) | UNIVERSAL | SOC 2 + PCI + ISO + NIST | Annual | AppSec
34 | AppSec | Software Bill of Materials (SBOM) | STANDARD-SPECIFIC | PCI 6.3.3 | Monthly | AppSec
35 | SysOps | Centralised logging (SIEM) | UNIVERSAL | SOC 2 + PCI + NIST | Continuous | SOC Lead
36 | SysOps | 12-month online log retention | DIFFERENTIATED | PCI strictest | Continuous | SOC Lead
37 | SysOps | File Integrity Monitoring (FIM) | MOSTLY-SHARED | SOC 2 + PCI + NIST | Weekly | SecOps
38 | SysOps | EDR everywhere incl. Linux | UNIVERSAL | SOC 2 + PCI + ISO + NIST | Continuous | IT
39 | SysOps | Email security + anti-phishing | MOSTLY-SHARED | SOC 2 + PCI 5.4.1 + ISO + NIST | Continuous | CISO + IT
40 | SysOps | Backup with AES-256 encryption + quarterly restore test | UNIVERSAL | All 5 | Quarterly | IT
41 | SysOps | Vulnerability scan (monthly) | UNIVERSAL | SOC 2 + ISO + NIST + PCI | Monthly | SecOps
42 | SysOps | Authenticated internal vulnerability scan | MOSTLY-SHARED | PCI 11.3.1.2 + SOC 2 | Quarterly | SecOps
43 | SysOps | Quarterly ASV scan (external) | STANDARD-SPECIFIC | PCI only | Quarterly | SecOps
44 | SysOps | Daily reconciliation of disbursements | STANDARD-SPECIFIC | SOC 2 PI + PCI Req 10 | Daily | Finance + Eng
45 | IR | Documented Incident Response Plan | UNIVERSAL | SOC 2 + PCI + NIST + RBI | Annual | CISO
46 | IR | Incident Response runbooks (P1-P4) | UNIVERSAL | SOC 2 + PCI + RBI | Per incident | SOC
47 | IR | RBI 2-hour notification mandate | STANDARD-SPECIFIC | RBI | Per incident | CISO + Legal
48 | IR | PCI acquirer notification within 24h | STANDARD-SPECIFIC | PCI | Per incident | CISO + Legal
49 | IR | DPDP 72h breach notification | STANDARD-SPECIFIC | DPDP | Per incident | DPO + Legal
50 | IR | CERT-In 6h notification | STANDARD-SPECIFIC | CERT-In | Per incident | CISO
51 | IR | Tabletop exercise 2x/year | UNIVERSAL | SOC 2 + ISO + NIST + RBI | Bi-annual | CISO
52 | DR | BCP / DR plan | UNIVERSAL | SOC 2 + PCI + ISO + NIST | Annual | CIO + CISO
53 | DR | Annual DR drill + RTO/RPO captured | UNIVERSAL | SOC 2 + PCI + ISO + NIST | Annual | IT + CISO
54 | DR | Backup integrity verification | MOSTLY-SHARED | SOC 2 + PCI + ISO | Quarterly | IT
55 | Change | Change Management Policy + CAB | UNIVERSAL | SOC 2 + PCI + ISO + NIST | Continuous | Engineering
56 | Change | Production access via JIT elevation | UNIVERSAL | SOC 2 + PCI + ISO + NIST | Continuous | IAM + Engineering
57 | Change | Emergency change SOP | MOSTLY-SHARED | SOC 2 + PCI + ISO + NIST | Continuous | Engineering
58 | Change | Pre-prod → Prod segregation | UNIVERSAL | SOC 2 + PCI + ISO + NIST | Continuous | Engineering
59 | Vendor | Service Provider Register | UNIVERSAL | SOC 2 + PCI + ISO + NIST | Quarterly | Compliance + CISO
60 | Vendor | Vendor SOC 2 + PCI AOC + ISO 27001 certs | UNIVERSAL | SOC 2 + PCI + ISO + NIST | Annual | Compliance
61 | Vendor | MSA with PCI acknowledgement clause | STANDARD-SPECIFIC | PCI 12.8 | Per vendor | Legal
62 | Vendor | Data Processing Agreement (DPA) | STANDARD-SPECIFIC | DPDP §10 + EU GDPR | Per vendor | Legal + DPO
63 | Vendor | Annual SOC 2 + PCI AOC expiry alerts | UNIVERSAL | SOC 2 + PCI + ISO | Continuous | Compliance
64 | Privacy | Privacy notice (web + mobile) | STANDARD-SPECIFIC | DPDP §4 + ISO A.5.34 + SOC 2 P1 | Annual | DPO + Legal
65 | Privacy | Consent receipt per data principal | STANDARD-SPECIFIC | DPDP §6 | Continuous | DPO + Eng
66 | Privacy | Data Principal Rights workflow | STANDARD-SPECIFIC | DPDP §8 | Continuous | DPO + Support
67 | Privacy | Records of Processing Activities (RoPA) | STANDARD-SPECIFIC | DPDP §11 + ISO A.5.34 | Quarterly | DPO
68 | Privacy | Cross-border transfer control (region lock) | STANDARD-SPECIFIC | DPDP §14 | Continuous | Cloud Lead
69 | Audit | Internal audit plan with 5-standard mapping | UNIVERSAL | SOC 2 + PCI + ISO + NIST + DPDP | Annual | Internal Audit
70 | Audit | Quarterly board pack | MOSTLY-SHARED | SOC 2 + PCI + ISO + RBI | Quarterly | CISO + CRO
71 | RBI | RBI Master Direction on Outsourcing 2021 | STANDARD-SPECIFIC | RBI | Annual | Compliance
72 | RBI | RBI IT Framework for NBFC 2023 | STANDARD-SPECIFIC | RBI | Annual | CISO
73 | RBI | RBI Cyber Security Framework 2023 | STANDARD-SPECIFIC | RBI | Continuous | CISO
74 | RBI | RBI Tokenisation Guidelines 2021 | STANDARD-SPECIFIC | RBI tokenisation | Continuous | CTO
75 | RBI | RBI Digital Lending Guidelines 2022 | STANDARD-SPECIFIC | RBI digital lending | Continuous | Product
76 | Training | Annual security training | UNIVERSAL | SOC 2 + ISO + NIST + RBI | Annual | CISO + HR
77 | Training | Quarterly phishing simulation | MOSTLY-SHARED | SOC 2 + PCI 5.4.1 + ISO + NIST | Quarterly | CISO + HR
78 | Physical | Badge + biometrics at facilities | UNIVERSAL | SOC 2 + PCI + ISO + NIST | Continuous | Facilities + CISO
79 | Physical | Visitor management | UNIVERSAL | SOC 2 + PCI + ISO + NIST | Continuous | Facilities
80 | Physical | POI / POS device monthly inspection | STANDARD-SPECIFIC | PCI Req 9 | Monthly | Operations
81 | Data Lifecycle | Data classification scheme | UNIVERSAL | SOC 2 + ISO + NIST + DPDP | Quarterly | DPO + CISO
82 | Data Lifecycle | Cardholder data storage inventory | STANDARD-SPECIFIC | PCI Req 3 | Quarterly | DPO
83 | Data Lifecycle | Auto-purge per retention | MOSTLY-SHARED | DPDP §7 + ISO A.8.10 | Continuous | Eng + DPO
84 | AI | AI/LLM risk assessment | MOSTLY-SHARED | DPDP + NIST + emerging EU AI Act | Annual | Product Security
85 | AI | Prompt injection defence controls | STANDARD-SPECIFIC | AI Act + OWASP Top 10 LLM | Quarterly | Product Security
86 | Prog | SteerCo charter | STANDARD-SPECIFIC | All standards governance | Annual | CISO + CRO
87 | Prog | GRC tooling (Vanta / Drata / Tugboat) | UNIVERSAL | SOC 2 + PCI + ISO + NIST | Continuous | CISO + IT
88 | Prog | Joint dashboard | UNIVERSAL | All 5 | Continuous | Compliance
89 | OT | OT/ICS risk register | MOSTLY-SHARED | ISO + NIST | Annual | CISO
90 | Quantum | Crypto agility roadmap (post-quantum) | STANDARD-SPECIFIC | NIST + emerging | Annual | Crypto Lead
91 | Cloud | Cloud Security Posture Management (CSPM) | MOSTLY-SHARED | SOC 2 + PCI + ISO + NIST | Continuous | Cloud Lead
92 | Cloud | AWS Config rules active | MOSTLY-SHARED | SOC 2 + PCI + ISO + NIST | Continuous | Cloud Lead
93 | Plan | Tabletop every 6 months | UNIVERSAL | SOC 2 + ISO + NIST + PCI | Bi-annual | SOC
94 | Plan | DR drill annually with documented RTO/RPO | UNIVERSAL | SOC 2 + PCI + ISO + NIST | Annual | IT + CISO
95 | Plan | Cybersecurity Committee meets Q | MOSTLY-SHARED | RBI §13 + ISO | Quarterly | Board
96 | Audit | SOC 2 Type II annual | STANDARD-SPECIFIC | SOC 2 only | Annual | CFO + CISO
97 | Audit | PCI ROC annual | STANDARD-SPECIFIC | PCI only | Annual | CFO + CISO + QSA
98 | Audit | ISO 27001 surveillance annual | STANDARD-SPECIFIC | ISO only | Annual | CFO + CISO + CB
99 | Audit | NIST CSF maturity assessment annual | STANDARD-SPECIFIC | NIST only | Annual | CISO + Internal Audit
100 | Audit | DPDP compliance self-attestation | STANDARD-SPECIFIC | DPDP | Annual | DPO + CISO

## 10 Policy Register
# | Document | Standards covered | Tag | Owner | Cadence
1 | Information Security Policy | All 5 | UNIVERSAL | CISO | Annual
2 | Risk Management Policy | All 5 | UNIVERSAL | CRO | Annual
3 | Acceptable Use Policy | SOC 2 + ISO + NIST | UNIVERSAL | CISO | Annual
4 | Code of Conduct | UNIVERSAL | UNIVERSAL | HR | Annual
5 | Background Verification Policy | SOC 2 + PCI + DPDP | UNIVERSAL | HR | On-hire
6 | Access Control Policy | All 5 | UNIVERSAL | CISO | Annual
7 | Authentication / MFA Policy | All 5 | UNIVERSAL | CISO + IAM | Annual
8 | Cryptographic Standards | All 5 | UNIVERSAL | Crypto Lead | Annual + on change
9 | Key Management Policy | SOC 2 + PCI + ISO | MOSTLY-SHARED | Crypto Lead | Annual
10 | Data Classification Policy | All 5 | UNIVERSAL | DPO + CISO | Annual
11 | Privacy Notice & Policy | DPDP + SOC 2 + ISO | STANDARD-SPECIFIC | DPO + Legal | Annual
12 | Consent Receipt Procedure | DPDP only | STANDARD-SPECIFIC | DPO | Continuous
13 | Data Principal Rights Workflow | DPDP only | STANDARD-SPECIFIC | DPO + Support | Continuous
14 | Cross-border Transfer Procedure | DPDP only | STANDARD-SPECIFIC | DPO + Cloud | Continuous
15 | Card Data Storage + Retention | PCI only | STANDARD-SPECIFIC | CISO + Compliance | Annual
16 | Cardholder Data Protection Policy | PCI only | STANDARD-SPECIFIC | CISO | Annual
17 | Network Security Policy | All 5 | UNIVERSAL | Network Lead + CISO | Annual
18 | Firewall / NSC Review Procedure | SOC 2 + PCI + ISO | UNIVERSAL | Network Lead | Bi-annual
19 | Secure Configuration Standards | SOC 2 + PCI + ISO + NIST | UNIVERSAL | Infra Lead | Annual
20 | Patch Management Policy | All 5 | UNIVERSAL | Infra Lead | Continuous
21 | Anti-Malware (EDR) Policy | All 5 | UNIVERSAL | CISO | Annual
22 | Anti-Phishing Programme | SOC 2 + PCI 5.4.1 + NIST | MOSTLY-SHARED | CISO | Quarterly
23 | Secure SDLC Policy | SOC 2 + PCI + ISO + NIST | UNIVERSAL | CTO | Annual + on change
24 | Payment Page Script Inventory Procedure | PCI 6.4.3 only | STANDARD-SPECIFIC | AppSec | Quarterly
25 | Change Management Policy | All 5 | UNIVERSAL | Engineering | Annual
26 | Logging & Monitoring Policy | SOC 2 + PCI + ISO + NIST | UNIVERSAL | CISO + SOC | Annual
27 | Audit Log Review Procedure | PCI + SOC 2 | MOSTLY-SHARED | SOC Manager | Daily + Weekly
28 | Time Synchronisation Procedure | SOC 2 + PCI + ISO | UNIVERSAL | Infra | Annual
29 | Vulnerability Management Policy | All 5 | UNIVERSAL | CISO | Annual
30 | ASV Scan Procedure | PCI only | STANDARD-SPECIFIC | SecOps | Quarterly
31 | Internal Vulnerability Scan Procedure | SOC 2 + PCI + ISO + NIST | UNIVERSAL | SecOps | Quarterly
32 | File Integrity Monitoring Procedure | SOC 2 + PCI + NIST | MOSTLY-SHARED | SecOps | Weekly
33 | Penetration Test Charter | SOC 2 + PCI + ISO + NIST | UNIVERSAL | AppSec | Annual
34 | Wireless + Rogue Device Procedure | PCI 11.2 only | STANDARD-SPECIFIC | SecOps | Annual
35 | Physical Security Policy (DC) | All 5 | UNIVERSAL | Facilities + CISO | Annual
36 | Visitor Management Procedure | All 5 | UNIVERSAL | Facilities | Daily
37 | POI / POS Device Inventory Procedure | PCI 9.5 only | STANDARD-SPECIFIC | Operations | Monthly
38 | Media Handling & Destruction | SOC 2 + PCI + ISO | UNIVERSAL | IT + Facilities | Continuous
39 | Security Awareness Training Policy | All 5 | UNIVERSAL | CISO + HR | Annual
40 | Mobile App Security Policy | SOC 2 + PCI + DPDP | UNIVERSAL | Mobile Security | Annual
41 | Personnel Security Policy | SOC 2 + PCI + ISO | UNIVERSAL | HR + CISO | Annual
42 | Service Provider Management Policy | SOC 2 + PCI + ISO | UNIVERSAL | CISO + Procurement | Annual
43 | Service Provider Register | All 5 | UNIVERSAL | Compliance | Quarterly
44 | MSA with PCI Acknowledgement | PCI only | STANDARD-SPECIFIC | Legal + Compliance | Per vendor
45 | Data Processing Agreement (DPA) | DPDP + ISO + SOC 2 | MOSTLY-SHARED | Legal + DPO | Per vendor
46 | Incident Response Plan | All 5 | UNIVERSAL | CISO | Annual
47 | IR Runbooks (P1-P4) | SOC 2 + PCI + RBI | MOSTLY-SHARED | SOC Manager | Per incident
48 | RBI 2-hour Notification Procedure | RBI only | STANDARD-SPECIFIC | CISO + Legal | Per incident
49 | DPDP 72-hour Breach Notification | DPDP only | STANDARD-SPECIFIC | DPO + Legal | Per incident
50 | BCP / DR Plan | All 5 | UNIVERSAL | CIO + CISO | Annual
51 | Risk Assessment Methodology | All 5 | UNIVERSAL | CRO + CISO | Annual
52 | Targeted Risk Analysis (TRA) Templates | PCI 4.0 only | STANDARD-SPECIFIC | CISO | Annual
53 | PCI Compliance Programme Summary | PCI only | STANDARD-SPECIFIC | Compliance | Annual
54 | SOC 2 Type II Programme Summary | SOC 2 only | STANDARD-SPECIFIC | Compliance | Annual
55 | ISO 27001 SoA | ISO only | STANDARD-SPECIFIC | CISO | Annual
56 | ISO 27001 RTP | ISO only | STANDARD-SPECIFIC | CISO | Annual
57 | Statement of Applicability | ISO only | STANDARD-SPECIFIC | CISO | Annual + on change
58 | Annual Compliance Maintenance Schedule | All 5 | UNIVERSAL | Compliance | Annual
59 | Quarterly Joint Compliance Dashboard | All 5 | UNIVERSAL | Compliance | Quarterly
60 | Cybersecurity Committee Charter | SOC 2 + RBI | MOSTLY-SHARED | Board Secretariat | Annual
61 | BYOD Policy | SOC 2 + ISO + NIST | UNIVERSAL | HR + CISO | Annual
62 | Work-from-Anywhere Policy | SOC 2 + ISO + NIST | UNIVERSAL | HR + IT + CISO | Annual
63 | Open Source Usage Policy | SOC 2 + ISO | UNIVERSAL | CTO + Legal | Annual
64 | Cyber Insurance Policy + Renewal | SOC 2 only | STANDARD-SPECIFIC | CFO + Legal | Annual
65 | AI/LLM Use Risk Policy | ISO + DPDP + NIST | MOSTLY-SHARED | Product Security | Annual
66 | OT/ICS Security Policy | ISO + NIST | MOSTLY-SHARED | CISO | Annual
67 | Post-quantum Crypto Migration | NIST | STANDARD-SPECIFIC | Crypto Lead | Annual
68 | Cloud Security Policy (CSPM) | All 5 | UNIVERSAL | Cloud Lead + CISO | Annual
69 | Outsourcing Policy (NBFC RBI) | RBI | STANDARD-SPECIFIC | Compliance + Legal | Annual
70 | 26AB Grievance Redressal (NBFC) | RBI | STANDARD-SPECIFIC | Customer Success | Annual

## 11 Project Plan
Week | Workstream | Standard | Task | Owner | Outcome
1 | Mobilise | All 5 | Charter + 5-standards SteerCo + PM appointment | CISO + CRO | Programme Charter
2 | Mobilise | All 5 | Auditor / QSA / Certification Body selection | CFO | Engagement letters
3-4 | Scoping | SOC 2 + PCI | System description + CDFD | CISO + Eng | SOC 2 System Desc + PCI CDFD
3-4 | Scoping | ISO 27001 | SoA initial + risk treatment plan | CISO | SoA v1.0
3-4 | Scoping | NIST CSF | Target profile + current profile assessment | CISO + Internal Audit | NIST profile v1.0
3-4 | Scoping | DPDP | Record of Processing Activities (RoPA) | DPO + DPO | RoPA v1.0
5-6 | Inventory | All 5 | Asset inventory + CDE + Privacy data flow | CISO + SecOps | Inventory live
5-8 | Scoping | All 5 | Joint gap assessment + tag assignment (Universal/Mostly-shared/Standard-specific/Differentiated) | CISO + Owners | Gap register
7-12 | TRA | PCI | Run TRA workshops for v4.0 mandatory requirements | CISO | TRA register
7-12 | Risk Assessment | ISO 27001 + NIST | Information security risk assessment + asset register | CISO + Risk | RA report
7-12 | DPIA | DPDP | DPIA for all significant data processing | DPO + DPO | DPIA register
8-20 | Remediation | All 5 | IAM + KMS + HSM + EDR + SIEM + WAF + ASV + GRC tool | Various | Tools configured
9-26 | Policies | All 5 | Write 70 documents; version control; owner ack | CISO + Owners | All 70 docs live
10-22 | Vendor | All 5 | AOC collection: SOC 2 + PCI + ISO + DPDP DPA | CISO + Procurement | Vendor pack
12-26 | Pen-test | PCI + SOC 2 + ISO | Annual pen-test; segmentation test (PCI) | AppSec | PT reports
22-32 | Dry Run | SOC 2 + PCI | Mock audit + sample pulls + interviews | CISO + PM | Internal ROC + readiness
22-32 | ASV | PCI | Q1 ASV scan + re-scan any failures | SecOps | ASV pass letter
24-36 | Audit | PCI | QSA fieldwork + ROC draft | QSA + CISO | ROC v1.0
24-36 | Audit | SOC 2 | Auditor fieldwork + Working Papers | Auditor + CISO | Working papers
26-38 | Audit | ISO 27001 | Certification Body Stage 1 + Stage 2 audit | CB + CISO | ISO 27001 cert
28-40 | Audit | NIST CSF | Internal maturity assessment | CISO + Internal Audit | NIST profile v2.0
30-40 | Issuance | PCI | AOC + ROC + acquirer filing | CISO + CFO | AOC delivered to acquirer
30-40 | Issuance | SOC 2 | Type II report issued | CISO + CFO | SOC 2 Type II
30-40 | Issuance | ISO 27001 | ISO 27001 certification | CISO + CFO | ISO cert
36-46 | Audit | DPDP | Self-attestation + third-party audit | DPO + External | DPDP attestation
40-50 | Surveillance | ISO 27001 | First surveillance audit (year 1) | CB + CISO | Surveillance OK
50-60 | Recertification | SOC 2 | Next SOC 2 Type II cycle | CISO + Auditor | SOC 2 year 2
52-65 | Recertification | PCI | Next PCI ROC | CISO + QSA | ROC year 2
60-72 | Continuous | All 5 | Quarterly dashboards + control health + GRC reporting | Compliance | Continuous
80+ | Maintenance | NIST | Annual maturity assessment | Internal Audit | Annual report

## 12 Evidence Catalog
# | Control | Standards | Frequency | Source | Tag | Pre-audit check
1 | Information Security Policy + acknowledgement | All 5 | Annual | LMS | UNIVERSAL | 100% signed
2 | Risk register + review minutes | All 5 | Quarterly | GRC | UNIVERSAL | Reviewed ≤90d
3 | BoD minutes on cyber | SOC 2 + ISO + NIST | Quarterly | Confluence | UNIVERSAL | On agenda
4 | SoA + RTP | ISO only | Annual | Confluence | STANDARD-SPECIFIC | Reviewed
5 | MFA enrolment | All 5 | Quarterly | Okta/Entra | UNIVERSAL | 100% CDE users
6 | IAM provisioning tickets | SOC 2 + PCI + ISO | Per request | Jira | UNIVERSAL | All approved
7 | Quarterly access reviews | SOC 2 + PCI + ISO | Quarterly | Confluence+IdP | MOSTLY-SHARED | All reviewed
8 | Card vault encryption attestation | PCI + ISO | Quarterly | AWS CloudHSM | MOSTLY-SHARED | Attestation current
9 | TLS scan A rating | SOC 2 + PCI + ISO | Quarterly | Qualys SSL | MOSTLY-SHARED | A or A+
10 | EDR coverage | All 5 | Continuous | CrowdStrike | UNIVERSAL | ≥99% fleet
11 | SIEM alert log + closure | SOC 2 + PCI + NIST | Continuous | Splunk | UNIVERSAL | MTTR within SLA
12 | 12-month log retention | PCI | Continuous | Splunk | DIFFERENTIATED | ≥12 months
13 | Quarterly ASV pass letter | PCI only | Quarterly | ASV vendor | STANDARD-SPECIFIC | Pass
14 | Internal vuln scan | SOC 2 + PCI + ISO + NIST | Quarterly | Tenable | UNIVERSAL | No criticals
15 | Pen-test report + segmentation | SOC 2 + PCI + ISO | Annual | PT vendor | UNIVERSAL | All scopes
16 | IRP + Tabletop minutes | All 5 | Annual | Confluence | UNIVERSAL | Tabletop 2x/year
17 | DR drill report | All 5 | Annual | Confluence + AWS | UNIVERSAL | RTO/RPO met
18 | CAB minutes + change tickets | All 5 | Weekly | Jira | UNIVERSAL | All prod
19 | SP register + AOCs + ISO certs | SOC 2 + PCI + ISO | Quarterly | Compliance | UNIVERSAL | AOC current
20 | MSA with PCI ack clause | PCI only | Per vendor | Legal | STANDARD-SPECIFIC | Signed
21 | DPA with data principals | DPDP only | Per vendor | Legal | STANDARD-SPECIFIC | Signed
22 | Consented receipt + withdrawal | DPDP only | Continuous | Backend | STANDARD-SPECIFIC | 100% captured
23 | Data Principal Rights workflow | DPDP only | Per request | Support | STANDARD-SPECIFIC | SLAs met
24 | RoPA | DPDP + ISO | Quarterly | DPO tool | MOSTLY-SHARED | Quarterly refresh
25 | Privacy notice version | DPDP + SOC 2 + ISO | Annual | Web + backend | STANDARD-SPECIFIC | Live
26 | Privacy training | All 5 | Annual | LMS | UNIVERSAL | ≥95% completion
27 | Phishing simulation results | SOC 2 + PCI 5.4.1 + NIST | Quarterly | KnowBe4 | MOSTLY-SHARED | ≥-50% phish-prone
28 | DPIA report | DPDP only | Per new processing | DPO | STANDARD-SPECIFIC | Completed
29 | TRA register | PCI 4.0 only | Annual | GRC | STANDARD-SPECIFIC | 12 TRAs
30 | Script inventory + SRI | PCI 6.4.3 | Weekly | AppSec | STANDARD-SPECIFIC | 100% authorised
31 | POI monthly inspection | PCI 9.5 | Monthly | Operations | STANDARD-SPECIFIC | All completed
32 | 3DS2 configuration | PCI 3DS2 | Continuous | Payments | STANDARD-SPECIFIC | Enabled
33 | SBI test | not standard | Annual | FPSB | STANDARD-SPECIFIC | (Optional SBI capability)
34 | BCP RTO/RPO profiling | All 5 | Annual | BIA | UNIVERSAL | Documented
35 | BCP tabletop | All 5 | Bi-annual | Confluence | UNIVERSAL | 2x/year
36 | Cyber insurance policy | SOC 2 only | Annual | CFO | STANDARD-SPECIFIC | In force
37 | Information security metrics dashboard | All 5 | Continuous | GRC | UNIVERSAL | Live
38 | Audit committee report | All 5 | Quarterly | CISO + CRO | UNIVERSAL | Submitted
39 | SAMA Gap analysis | SOC 2 + ISO + NIST | Annual | CISO | MOSTLY-SHARED | Annual
40 | Vendor incident coordination | All 5 | Per incident | Compliance | UNIVERSAL | Acknowledgement <24h
41 | Crypto agility assessment | NIST only | Annual | Crypto Lead | STANDARD-SPECIFIC | PQC roadmap
42 | AI/LLM risk assessment | DPDP + NIST | Annual | Product Security | MOSTLY-SHARED | TRA filed
43 | Lab Inventory / SBOM | PCI 6.3.3 | Monthly | AppSec | STANDARD-SPECIFIC | Per release
44 | Annual compliance schedule | All 5 | Annual | Compliance | UNIVERSAL | Cover all 5
45 | RBI Cyber Security Reporting Register | RBI only | Continuous | Compliance | STANDARD-SPECIFIC | SLA met
46 | RBI Master Direction Outsourcing Register | RBI only | Continuous | Compliance | STANDARD-SPECIFIC | Reviewed
47 | RBI Tokenisation Compliance | RBI only | Continuous | CTO | STANDARD-SPECIFIC | CoF tokenised
48 | Certificate inventory | All 5 | Continuous | Crypto Lead | UNIVERSAL | Renewed
49 | Customer comms test (status page) | SOC 2 + ISO | Continuous | StatusPage | MOSTLY-SHARED | Verified
50 | Audit log review aging | SOC 2 + PCI | Continuous | SOC | UNIVERSAL | <24h

## 13 Vendors
# | Vendor | Service | SOC 2 | PCI | ISO | DPDP | Risk | Owner
1 | AWS India | Hosting/KMS/CloudHSM | Yes | Yes (SP L1) | Yes | DPA | Low | Cloud Lead
2 | Okta | SSO + WebAuthn | Yes | n/a | Yes | DPA | Low | IAM Lead
3 | CyberArk | PAM | Yes | n/a | Yes | n/a | Low | IAM Lead
4 | CrowdStrike | EDR | Yes | n/a | Yes | n/a | Low | SecOps
5 | Splunk | SIEM | Yes | Yes (PCI attested) | Yes | n/a | Low | SOC Lead
6 | Tenable | Vulnerability scanner | Yes | Yes | Yes | n/a | Low | SecOps
7 | ASV (Trustwave / CyberOxide) | Quarterly ASV | n/a | Yes | n/a | n/a | Low | SecOps
8 | Visa Token Service (VTS) | Tokenisation | n/a | Yes | n/a | n/a | Low | CTO
9 | Mastercard MDES | Tokenisation | n/a | Yes | n/a | n/a | Low | CTO
10 | RuPay Token Vault | Tokenisation (IN) | n/a | Yes | n/a | n/a | Low | CTO
11 | Razorpay / Cashfree / Adyen | Payment gateway | Yes | Yes | Yes | DPA | Low | CTO
12 | Pine Labs / Innoviti | P2PE POS | n/a | Yes (P2PE) | n/a | n/a | Low | Operations
13 | AuthBridge / HireRight | BGV | Yes | n/a | n/a | n/a | Low | HR
14 | KnowBe4 / Hoxhunt | Phishing sim | Yes | n/a | Yes | n/a | Low | CISO
15 | Bajaj Finance / ICICI | Co-issuer bank | n/a | Yes | Yes | DPA | Med | CTO
16 | Signzy / Perfios | eKYC V-CIP | Yes | No (no CHD) | Yes | n/a | Med | Product
17 | Pen-test vendor (NCC / NetSPI) | Pen-test | Yes | Yes | Yes | n/a | Low | AppSec
18 | Collection agencies | Field collection | Yes | No (no CHD) | n/a | DPA | High | Compliance
19 | Big-4 Audit firm | SOC 2 + ISO | Yes | Yes | Yes | n/a | Low | CFO
20 | Tier-1 QSA firm | PCI ROC | Yes | Yes | Yes | n/a | Low | CFO + CISO
21 | CIBIL / Experian / Equifax | Credit bureau | Yes | n/a | n/a | DPA | Med | Credit Risk
22 | AI / LLM provider | Provider LLM | Yes | n/a | Yes | DPA | Med | Product
23 | Translation vendor | Localization | Yes | n/a | n/a | DPA | Low | Marketing
24 | Backup vendor (NetApp) | Backup + DR | Yes | Yes | Yes | n/a | Low | IT
25 | AV / Anti-malware | EDR alternative | Yes | Yes | Yes | n/a | Low | IT

## 14 Audit Trail Q&A
# | Category | Question | Answer | Source tab
1 | Common | How do 5 standards run together? | Same SteerCo, same evidence repo, dedicated tag per control. Triple-tagged evidence: SOC 2 + PCI + ISO + NIST + DPDP refs in each file's YAML. | 09 + Tab 03
2 | Common | Cost saving vs five separate programmes? | ~40% engineer-hour reduction; audit fees from ₹5+ crore/y to ₹3+ crore/y joint headline cost; 8 dashboards collapse to 1. | Joint PDF + 11 Plan
3 | Common | How many controls total? | ~100 deduped controls from >250 raw requirements across 5 standards. ~50% dedupe rate achievable. | 09 Checklist
4 | Common | Biggest engineering hour saver? | Identity & Access: single Okta + WebAuthn replaces 5 standards' onboarding workflows. Saves ~28% total.09 Task 9-15
5 | SOC 2 | TSC set chosen | Security, Availability, Confidentiality, Processing Integrity. Privacy deferred to 2026 cycle. | SOC 2 PDF
6 | SOC 2 | Type II timing | 12-month window aligned with RBI fiscal year (Apr-Mar) or Jan-Dec per board preference. | SOC 2 PDF
7 | PCI | Service provider Level 1? | Yes; 2.6M cards in vault; ROC by Tier-1 QSA; quarterly ASV by Trustwave India. | PCI PDF
8 | PCI | Tokenisation per RBI? | CoF all tokenised via VTS/MDES/R-T-V; >98% redaction on store. Reduces effective PCI scope by ~28%. | PCI PDF
9 | PCI | TRA register — how many? | 12 TRAs in active register; reviewed annually + on material change. | PCI PDF + 12
10 | DPDP | SDF obligations | Significant Data Fiduciary provisions triggered >vol> annual retention; DPIA needed for >large scale special category. | DPDP PDF + 04
11 | DPDP | 72-hour breach | Yes - 72h to data principals; 2h to RBI for severe incidents; parallel clocks governed via single IRP. | DPDP PDF + 08
12 | DPDP | Cross-border lock | Region lock to ap-south-1 + ap-southeast-1; no transfer to non-notified countries. | 04 + Sheet 4
13 | ISO 27001 | SoA kept? | Yes; A.5 increments across all 93 Annex A controls. Aerated annual. | 05 + 10
14 | ISO 27001 | Internal audit programme | Yes; 3-yr cycle; cover all 5 standards' clauses. | 05 + 14
15 | NIST CSF | 2.0 changes | Added Govern function; expanded DE.AE/DE.CM; added GV.SC; mandates integrated risk. | 06
16 | NIST CSF | Target profile? | Tier 3 → 4 trajectory; biannual maturity assessment. | 06 + 11
17 | Cross | Which framework unifies? | NIST CSF 2.0 since RBI IT Framework 2023 maps closely to NIST 800-53 + CSF | 06 + 02
18 | Cross | Single evidence index | Each file has YAML header 'tsp_id','pci_req','iso','nist','dpdp' fields. GRC tool indexes. | Joint PDF
19 | Cross | Joint calendar | PC Sep-Oct / SOC 2 Jan-Feb / ISO 27001 Stage 1 in Q1, Stage 2 in Q2 / NIST in Q3 / DPDP in Q4. | Joint PDF + 11
20 | Cross | AOC expiry alerts | Auto alert 60/30/15 days pre-expiry. SP register refreshed quarterly. | 13 + 09
21 | NBFC | RBI Cyber Committee met? | Quarterly; chaired by MD/CEO; minutes circulated. | Sheet 02 + 10
22 | NBFC | DPDP SDF obligations met? | DPIA again for any new product launch (e.g., co-lending card product). | 04 + 09
23 | NBFC | CIBIL data classification | Confidential tier; last-4 only in non-CDE stores; full pull logs in vault. | 09 + 13
24 | NBFC | Field collection agency risk | High risk; AOCs received + DPA signed + TRA done + quarterly audit rights. | 13
25 | Cost | Auditor fees combined | SOC 2 ₹12-25 lakh + PCI ROC ₹18-50 lakh + ISO surveillance ₹10-25 lakh + NIST maturity ₹5-10 lakh = ₹45-110 lakh/yr | Joint PDF
26 | Cost | Engineer-hour saving | Approx 2,000 engineer-hours saved annually vs 5 separate programmes. | Joint PDF
27 | Cost | GRC tool annual cost | Vanta ₹35-65 lakh/yr; Drata ₹30-55 lakh; Tugboat cheaper. | Joint PDF
28 | Risk | Biggest implementation risk? | Parallel deadlines; AOC expiry slippage; DPDP penalty exposure. | Risk Plan
29 | Risk | Mitigation | Quarterly CISO review; auto calendar; quarterly board report. | Risk Plan
30 | Tool | Single evidence repository | S3 versioning + locking; manifests per TSC + PCI Req + ISO Annex + NIST Subcategory + DPDP §. | 12 evidence catalog
31 | Tool | Sample pull cadence | 30-40 per control per standard; cross-tagging in evidence file metadata. | 12
32 | Tool | Cross framework dashboards | Vanta + custom Power BI / Tableau dashboards; weekly refresh. | Joint PDF
33 | Tool | Pen-test vendor | Single NCC Group / NetSPI covers SOC 2 + PCI + ISO + NIST tests in one statement of work. | Joint PDF
34 | Maintenance | Annual work | Q1 SOC 2 renewal; Q2 ISO surveillance; Q3 PCI ROC start; Q4 NIST maturity. | 11
35 | Maintenance | Quarterly work | Quarterly CCO committee + AOC expiry check + control health pull. | 11
36 | Vendor | Vendor pyramid | AWS + Azure (T-II SaaS) + cyber tools (T-II SaaS); token + payment ecosystem (T-II PCI). | 13
37 | Vendor | Manage 25+ vendors | Quarterly CISO review; automated calendar reminders; annual onsite review for critical 5. | 13
38 | Vendor | Risks of SP consolidation | Single source of truth risk on centralised services (e.g., Okta). | 13
39 | Process | SteerCo meetings | Monthly operational + Quarterly SteerCo with Board Cyber Committee. | Joint PDF
40 | Process | Auditor rotation | Rotate auditor + QSA + CB every 5 years for independence. | Joint PDF